## CMS
ID | Page | Sub Menu | Feature | Bobot | Test | Action | Step | Expected Result | Actual Result | Status | Progress | Remarks of Test
CMS-001 | CMS | Orders | Shipped by Courier | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-002 | CMS | Orders | Pick Up in Store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-003 | CMS | Orders | On Going | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-004 | CMS | Orders | All Transaction | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-005 | CMS |  | [CMS] CMS pick up order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-006 | CMS |  | [INTEGRASI] Wording breadcrumb di order detail disamakan dengan Order ID | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-007 | CMS |  | [INTEGRASI] Cancel order - Memunculkan pop up alasan cancel dan mengubah status order menjadi Cancelled | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-008 | CMS |  | [BACKEND] Sort by default order list dibuat berdasarkan order terbaru | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-009 | Login |  | Resetting Password | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
CMS-010 | Login |  | Resetting Password - Link Sent | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
CMS-011 | My Account |  | Account Settings | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
CMS-012 | CMS | Dashboard | Dashboard | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-013 | CMS | Brands | Brands | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-014 | CMS | Payment Methods | Payment Methods | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-015 | CMS | Category Product | Category | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-016 | CMS | Category Product | Sub Category | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-017 | CMS | Location Store | Location Store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-018 | CMS | Store | Store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100 | Untuk tombol READ / VIEW saat ini masih digunakan untuk redirect ke halaman CMS store
CMS-019 | CMS | Admin | Admin | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-020 | CMS | Privilege | Privilege | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-021 | CMS | Setting | Setting | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-022 | CMS | Newsroom | Newsroom | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-023 | CMS | User | User | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-024 | CMS | Documentation | Documentation | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-025 | CMS | CMS Store | CMS Store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-026 | CMS | Menu List | Sub Menu | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100 | Notes
CMS-027 | CMS | Menu List | Menu List | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-028 | CMS | Dashboard | Dashboard | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-029 | CMS | Store Owner | Store Owner | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-030 | CMS | Privilege | Privilege | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-031 | CMS | Product | Product | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-032 | CMS | Special Price | Special Price | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100 | Untuk menu ini akan dihapus dari list menu & dijadikan fitur di menu Product
CMS-033 | CMS | CMS Utama ( Figma ) | CMS Utama ( Figma ) | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-034 | CMS | Menu List | Sub Menu | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100 | Notes
CMS-035 | CMS | Menu List | Menu List | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-036 | CMS | Dashboard | Dashboard | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-037 | CMS | Product | All Products | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-038 | CMS | Product | Category | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-039 | CMS | Product | Brands | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-040 | CMS | Customer | Customer | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-041 | CMS | Vouchers | Vouchers | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-042 | CMS | Vouchers | View Voucher Usage | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-043 | CMS | Newsroom | Newsroom | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-044 | CMS | Store | Store List | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-045 | CMS | Store | Location | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-046 | CMS | Transaction Report | Transaction Report | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-047 | CMS | Admin | Admin | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-048 | CMS | Privilege | Privilege | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-049 | CMS | General Settings | Company | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-050 | CMS | General Settings | Payment Methods | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-051 | CMS | General Settings | Shipping Methods | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-052 | CMS | OTP Logs | OTP Logs | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100 | ada tombol action ( Send OTP )
CMS-053 | CMS | Documentation | Documentation | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-054 | CMS | CMS Store ( Figma ) | CMS Store ( Figma ) | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-055 | CMS | Menu List | Sub Menu | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100 | Notes
CMS-056 | CMS | Menu List | Menu List | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-057 | CMS | Dashboard | Dashboard | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-058 | CMS | Product | All Product | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-059 | CMS | Product | Special Price | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-060 | CMS | Store Owner | Store Owner | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-061 | CMS |  | [CMS] Menambahkan Menu Admin | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-062 | CMS |  | [CMS] Menambahkan Menu Privilege | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-063 | CMS |  | [CMS] Menambahkan Menu Settings | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-064 | API |  | [API] Account Settings | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-065 | CMS |  | [CMS] Menambahkan master data location | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-066 | CMS |  | [CMS] Menambahkan Menu Newsroom | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-067 | CMS |  | [CMS] Membuat menu Brand | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-068 | CMS |  | [CMS] Membuat fitur import excel special price list | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-069 | UI/UX |  | [UI/UX] Membuat design CMS Pusat & CMS Store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-070 | CMS |  | [CMS] Membuat menu Payment Method | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-071 | CMS |  | [CMS] Membuat menu Data User | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-072 | SLICING |  | [Slicing] Page Account Setting | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-073 | INTEGRASI |  | [Integrate] Account + Account Setting + Addresses | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-074 | CMS |  | [CMS] Pengembangan modul Voucher usage amount di CMS | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-075 | CMS |  | [CMS] Penambahan tampilan warning Pick Up Bandara. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-076 | CMS |  | [CMS] Update discover handmade treasure dengan fotonya juga melalui CMS/General settings/Content | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-077 | CMS |  | [CMS] Update 3 Banner di homepage login di CMS, dengan update textnya juga tapi tidak mandatory | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-078 | CMS |  | [CMS] Master data page info | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-079 | CMS |  | [SLICING] Fix icon show password naik saat digunakan | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-080 | CMS |  | [INTEGRASI] Membedakan header guess dan login | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-081 | CMS |  | [INTEGRASI] Integrasi Kategori & Sub kategori | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-082 | CMS |  | [INTEGRASI] Integrasi Filters | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-083 | CMS |  | {API} Fixing pagination Newsroom | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-084 | CMS |  | [API] Fix localization agar lebih seragam | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-085 | CMS |  | [SLICING} Responsive Shopping bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-086 | CMS |  | [INTEGRASI] Shopping bag, penambahan validasi kalau pilih 2 store berbeda | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-087 | CMS |  | [INTEGRASI] Checkout, Validasi jika lokasi store bandara maka akan muncul warning di address toko | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-088 | CMS |  | [INTEGRASI] Other fee, untuk biaya admin bank dan biaya tambahan, pengaturan bisa langsung via channel bank | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-089 | CMS |  | [INTEGRASI] Download Invoice | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-090 | CMS |  | [INTEGRASI] Button pay now | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-091 | CMS |  | [INTEGRASI] Bahasa id/en newsroom & newsroom detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-092 | CMS |  | [INTEGRASI] Icon payment method | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-093 | CMS |  | [API] Menambahkan flaggin isTrulyIndonesia, isLimited, dan isDiscount | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
CMS-094 | CMS |  | [CMS] Update max character limit untuk CMS Content - Privacy policy dan terms&condition | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100

## Frontend
ID | Page | Sub Menu | Feature | Bobot | Test | Action | Step | Expected Result | Actual Result | Status | Progress | Remarks of Test
FE-001 | General |  | How to order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-002 | Profile |  | Order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-003 | Profile |  | How to Order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-004 | Shopping Bag |  | Order Summary | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-005 | Checkout |  | Order Summary | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-006 | Order List Page |  | Order Filter by Status | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-007 | Order List Page |  | Order Filter by Date | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-008 | Order List Page |  | Product list info | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-009 | Order List Page |  | Order Search | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-010 | Order List Page |  | Order List Status - Pickup Store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-011 | Order List Page |  | Order List Status - Delivery Shipping | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-012 | Order List Page |  | CTA Pay Now | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-013 | Order List Page |  | CTA Buy Again | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-014 | Order List Page |  | CTA Cancel order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-015 | Order Detail |  | Info Transaksi | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-016 | Order Detail |  | Status Order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-017 | Order Detail |  | List Product | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-018 | Order Detail |  | Info payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-019 | Order Detail |  | Info Delivery Address | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-020 | Order Detail |  | CTA Buy Again | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-021 | Order Detail |  | CTA Pay Now | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-022 | Order Detail |  | Presentase | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-023 | UI/UX |  | [UI/UX] Membuat design menu How to Order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-024 | API |  | [API] Membuat API Order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-025 | SLICING |  | [Slicing] Empty State Order List | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-026 | SLICING |  | [Slicing] Page Order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-027 | SLICING |  | [Slicing] Page Order Detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-028 | UI/UX |  | [UI/UX] Menambahkan Due Date pada order yang masih status waiting for payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-029 | UI/UX |  | [UI/UX] Penambahan indikator tipe delivery, Ship by Courier & Pick up in Store di halaman list "Order" | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-030 | UI/UX |  | [UI/UX] UI adjustment di halaman Order Detail, List item di kategorikan berdasarkan brand | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-031 | UI/UX |  | [UI/UX] Menambahkan tombol "Order Again" untuk halaman Order Detail dengan status yang completed | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-032 | SLICING |  | [Slicing] Cancel Order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-033 | SLICING |  | [Slicing] Revisi Order List | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-034 | SLICING |  | [Slicing] Revisi Order Detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-035 | API |  | [API] Detai Order masih ada data yang 0, Summary saat checkout dan waiting payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-036 | API |  | [API] ORDER LIST, DETAIL ORDER BANYAK PENYESUAIAN, SESUAIKAN untuk order listnya | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-037 | API |  | [API] COUNTING, KAK GEDE BUTUH DI PROFILE, ORDER & VOUCHER, UNTUK COUNTING VOUCHER DIBUAT GENERAL SAJA UNTUK SEMUA VOUCHER | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-038 | INTEGRASI |  | [Integrasi] Order List | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-039 | UI/UX |  | [UI/UX] Menambahkan button order again di 'order detail - completed' | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-040 | UI/UX |  | [UI/UX] Menambahkan button pay now & cancel order di 'order detail - waiting for payment' | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-041 | SLICING |  | [Slicing] Validasi notification order & update | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-042 | INTEGRASI |  | [Integrasi] Order list | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-043 | INTEGRASI |  | [Integrasi] Order Detail (Pickup in store) | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-044 | SLICING |  | [Slicing] Update tampilan cancel order, menampilkan textbox untuk opsi others | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-045 | SLICING |  | [Slicing] Penambahan button & Validasi fitur Buy di halaman Order list/Order detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-046 | INTEGRASI |  | [Integrasi] Cancel Order — penyesuaian perubahan status pada Orders. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-047 | INTEGRASI |  | [Integrasi] Fitur buy again pada order list/order detail (menunggu API dari backend) | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-048 | API |  | [Backend] Perubahan penamaan Order Number. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-049 | API |  | [API] Penambahan API Change Payment di Order Detail. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-050 | API |  | [API] Fitur Cancel Order — penambahan payload | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-051 | API |  | [API] Firebase Notification — perhitungan total Order dan Voucher. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-052 | API |  | [API] Perbaikan API Order Detail. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-053 | UI/UX |  | [UI/UX] Order detail - Penambahan status order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-054 | UI/UX |  | [UI/UX] Order list - Penambahan chip component untuk status order | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-055 | SLICING |  | [SLICING] Responsive order detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-056 | UI/UX |  | [UI/UX] Order complete pada order list ubah jadi warna hijau | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-057 | SLICING |  | [SLICING] Order complete pada order list ubah jadi warna hijau | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-058 | UI/UX |  | [UI/UX] Postal code di onboarding | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-059 | SLICING |  | [SLICING] Postal code di onboarding | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-060 | Home (Guess) |  | Home | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-061 | Home (Guess) |  | Sign Up | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100 | top bar dibuat memunculkan languange, sarinah care, dan how to order saja pada tampilan mobile
FE-062 | Home (Guess) |  | OTP | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-063 | Home (Guess) |  | Set Up Password | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-064 | Home (Guess) |  | You're All Set | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-065 | Home (Guess) |  | Onboarding | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-066 | Login |  | Recover Password | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-067 | General |  | Language | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-068 | General |  | Indonesia | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-069 | General |  | Inggris | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-070 | General |  | Newsroom | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-071 | General |  | Newsroom detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-072 | General |  | All Categories | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-073 | General |  | Page Not Found | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-074 | General |  | Error Page | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-075 | General |  | Terms of Service | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-076 | General |  | Privacy Policy | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-077 | General |  | Footer | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-078 | General |  | Email Newsletter | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-079 | General |  | Social Media Button | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-080 | General |  | Maintenance Mode | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-081 | General |  | Wishlist | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-082 | General |  | Sarinah Club | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-083 | Profile |  | Account | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-084 | Profile |  | Voucher | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-085 | Profile |  | Log Out | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-086 | Notification |  | Integrasi | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-087 | Search Bar |  | Search Result | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-088 | Search Bar |  | Search result empty | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-089 | Cart |  | Shopping Bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-090 | Product Detail |  | Product Detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-091 | Product Detail |  | Size Chart | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-092 | Product Detail |  | Color | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-093 | Product Detail |  | Quatites | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-094 | Product Detail |  | Image Gallery | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100 | - pas zoom foto ke 2 dst, yang ditampilkan foto ke 1 terus
FE-095 | Product Detail |  | Image Preview | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-096 | Product Detail |  | Description | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-097 | Product Detail |  | Style Section | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50 | Phase pengerjaan berikutnya
FE-098 | Product Detail |  | Review Section | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50 | Phase pengerjaan berikutnya
FE-099 | Product Detail |  | Review Section - Rating | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50 | Phase pengerjaan berikutnya
FE-100 | Product Detail |  | CTA Add to Shopping bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-101 | My Account |  | Account Home | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-102 | My Account |  | Account Address | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-103 | Shopping Bag |  | Title Store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-104 | Shopping Bag |  | List Item Product | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-105 | Shopping Bag |  | Edit Quatities | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-106 | Shopping Bag |  | Delete Product | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-107 | Shopping Bag |  | Out of Stock Product | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-108 | Shopping Bag |  | CTA "to Checkout" | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-109 | Checkout |  | Title Store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-110 | Checkout |  | List Item Product + Pricing | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-111 | Checkout |  | Shipping by Courier | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-112 | Checkout |  | Pickup in Store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-113 | Checkout |  | Delivery Address | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50 | masih proses registrasi shipping dengan lazada express
FE-114 | Checkout |  | Payment Method - Payment Gateway | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100 | masih menggunakan milik unictive
FE-115 | Checkout |  | Add Voucher | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-116 | Payment Page |  | Confirmation Payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-117 | Payment Page |  | Confirmation Payment - CTA Check Status | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-118 | Payment Page |  | Succesfully Payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-119 | Payment Page |  | Unsuccesfully Payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-120 | Payment Page |  | Expired Payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected |  | IN PROGRESS | 50
FE-121 | API |  | [API] Update Profile | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-122 | API |  | [API] Onboarding | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-123 | API |  | [API] Check Onboarding | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-124 | SLICING |  | [Slicing] Page Home User Non Login | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-125 | SLICING |  | [Slicing] Page Home User Login | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-126 | SLICING |  | [Slicing] Page Sign Up | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-127 | SLICING |  | [Slicing] Page OTP | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-128 | SLICING |  | [Slicing] Page Set Up Password | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-129 | SLICING |  | [Slicing] Page Success Set Up Password | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-130 | SLICING |  | [Slicing] Page Onboarding - Welcome | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-131 | SLICING |  | [Slicing] Page Onboarding - About | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-132 | SLICING |  | [Slicing] Page Onboarding - Interest | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-133 | SLICING |  | [Slicing] Page Onboarding - Thank You | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-134 | SLICING |  | [Slicing] Page Forget Password | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-135 | API |  | [API] Membuat API Product Home Banner | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-136 | API |  | [API] Membuat API Newsroom | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-137 | UI/UX |  | [UI/UX] Menambahkan background putih di favicon | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-138 | UI/UX |  | [UI/UX] Menambahkan form dengan field alamat pada halaman onboarding | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-139 | SLICING |  | [Slicing] Page Product | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-140 | INTEGRASI |  | [Integrate] Sign Up & OTP | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-141 | INTEGRASI |  | [Integrate] Login Email & Google | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-142 | INTEGRASI |  | [Integrate] Onboarding | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-143 | UI/UX |  | [UI/UX] Membuat tampilan error condition | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-144 | API |  | [API] Membuat API Provinsi & Kota | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-145 | UI/UX |  | [UI/UX] Menyeragamkan nama toko menjadi dibawah rating & total sold item | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-146 | UI/UX |  | [UI/UX] Adjustment pada header before & after login | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-147 | SLICING |  | [Slicing] Pop Up All Category | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-148 | UI/UX |  | [UI/UX] Menu Newsroom | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-149 | UI/UX |  | [UI/UX] Pop up Profile | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-150 | SLICING |  | [Slicing] Membuat dropdown notification | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-151 | SLICING |  | [Slicing] Pop Up Shopping Bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-152 | SLICING |  | [Slicing] Membuat dropdown profile | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-153 | SLICING |  | [Slicing] Newsroom | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-154 | UI/UX |  | [UI/UX] Membuat design menu Wishlist | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-155 | SLICING |  | [Slicing] Page Newsroom Detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-156 | INTEGRASI |  | [Integrate] Data Profile Header | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-157 | INTEGRASI |  | [Integrate] Log out | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-158 | SLICING |  | [Slicing] Page Product Detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-159 | UI/UX |  | [UI/UX] Membuat design menu Voucher | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-160 | UI/UX |  | [UI/UX] Membuat design Page Term of Use & Privacy Policy | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-161 | SLICING |  | [Slicing] Pop Up Size Chart | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-162 | SLICING |  | [Slicing] Page Account Home | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-163 | SLICING |  | [Slicing] Page Account Addresses | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-164 | SLICING |  | [Slicing] Page Change Email Preference | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-165 | SLICING |  | [Slicing] Page Change Password | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-166 | SLICING |  | [Slicing] Page Shopping Bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-167 | SLICING |  | [Slicing] Page Checkout | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-168 | SLICING |  | [Slicing] Page Waiting for Payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-169 | SLICING |  | [Slicing] Page Payment Successful | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-170 | API |  | [API] Membuat API Shopping Bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-171 | INTEGRASI |  | [Integrate] Home - Before Login | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-172 | INTEGRASI |  | [Integrate] Home - After Login | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-173 | INTEGRASI |  | [Integrate] Pop Up Size Chart | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-174 | API |  | [API] Membuat API Payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-175 | INTEGRASI |  | [Integrate] Product - Detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-176 | INTEGRASI |  | [Integrate] Shopping Bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-177 | INTEGRASI |  | [Integrate] Pop Up All Category + Pop Up Shopping Bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-178 | UI/UX |  | [UI/UX] Menambahkan button "start shopping" pada design empty state shopping bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-179 | UI/UX |  | [UI/UX] Empty state shopping bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-180 | UI/UX |  | [UI/UX] Pop up delete cart di shopping bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-181 | UI/UX |  | [UI/UX] Share product detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-182 | UI/UX |  | [UI/UX] Flow pick up store di bandara | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-183 | UI/UX |  | [UI/UX] Button "Start Shopping" di empty state shopping bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-184 | UI/UX |  | [UI/UX] Payment Option QRIS diubah menjadi radio button dan langsung menunjukan QR | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-185 | UI/UX |  | [UI/UX] Flow pick up store di bandara | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-186 | INTEGRASI |  | [Integrasi] Recommendation Product (After Login) | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-187 | INTEGRASI |  | [Integrasi] Shopping Bag Out Of Stock | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-188 | SLICING |  | [Slicing] Revisi tampilan diskon di relayout ke atas | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-189 | SLICING |  | [Slicing] Empty State Shopping Bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-190 | SLICING |  | [Slicing] Pop up Remove Product | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-191 | SLICING |  | [Slicing] Page Reset password - Link send | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-192 | INTEGRASI |  | [Integrate] Checkout | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-193 | INTEGRASI |  | [Integrate] Waiting for payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-194 | INTEGRASI |  | [Integrate] Counting Notification Shopping Bag | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-195 | UI/UX |  | [UI/UX] Hapus flow 'Change' di change password | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-196 | UI/UX |  | [UI/UX] Menambahkan UI checkout dengan metode pembayaran retail outlet | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-197 | UI/UX |  | [UI/UX] UI wording untuk pembayaran metode QRIS | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-198 | UI/UX |  | [UI/UX] UI halaman "Shopping Bag" dengan case 1 product dengan case out of stock | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-199 | UI/UX |  | [UI/UX] Menambahkan design how to pay untuk semua metode pembayaran yang masih belum ada designnya | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-200 | SLICING |  | [Slicing] Payment Method QRIS | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-201 | SLICING |  | [Slicing] Payment Expired | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-202 | SLICING |  | [Slicing] Page Error 404 | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-203 | SLICING |  | [Slicing] Page Error Maintanace | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-204 | SLICING |  | [Slicing] Search bar - Search result | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-205 | SLICING |  | [Slicing] Search bar - Empty Result | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-206 | SLICING |  | [Slicing] Change Payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-207 | SLICING |  | [Slicing] clickable Preview image di product detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-208 | SLICING |  | [Slicing] Add Voucher - Hilangkan tampilan preview | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-209 | API |  | [API] SAMPLE DATA SUCCESS, EXPIRED/FAILED, CANCEL PAYMENT | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-210 | UI/UX |  | [UI/UX] Membuat Design Invoice | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-211 | UI/UX |  | [UI/UX] menambahkan button start shopping di shopping bag jika barang yang masuk shopping bag menjadi out of stock | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-212 | UI/UX |  | [UI/UX] how to pay untuk setiap metode payment (VA, CC, dan QRIS) | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-213 | UI/UX |  | [UI/UX] tambahkan watermark 'paid' & 'unpaid' di invoice | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-214 | SLICING |  | [Slicing] Revisi tampilan Pop Up Promo | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-215 | SLICING |  | [Slicing] Validasi promo kosong | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-216 | SLICING |  | [Slicing] Revisi tampilan pop up list address | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-217 | SLICING |  | [Slicing] searchbar | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-218 | SLICING |  | [Slicing] searchbar no result | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-219 | SLICING |  | [Slicing] keep exploring diberikan validasi jika tidak ada productnya maka tidak dimunculkan | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-220 | SLICING |  | [Slicing] Tooltip Other fees | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-221 | SLICING |  | [Slicing] Page search result | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-222 | SLICING |  | [Slicing] page search result empty | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-223 | SLICING |  | [Slicing] perbaikan menu header tidak overlay | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-224 | INTEGRASI |  | [Integrasi] notification (counting dengan Firebase & list menggunakan API) | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-225 | INTEGRASI |  | [Integrasi] mark all as read | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-226 | INTEGRASI |  | [Integrasi] Adjustment shopping bag, grouping per toko, per brand , dan per product | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-227 | INTEGRASI |  | [Integrasi] Adjustment checkout struktur | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-228 | INTEGRASI |  | [Integrasi] waiting payment | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-229 | INTEGRASI |  | [Integrasi] payment expired | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-230 | INTEGRASI |  | [Integrasi] payment success | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-231 | UI/UX |  | [UI/UX] Shopping bag Grouping Out of stock | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-232 | UI/UX |  | [UI/UX] Button Checkout dihapus di cart | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-233 | UI/UX |  | [UI/UX] Penambahan placeholder untuk gambar kosong | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-234 | SLICING |  | [Slicing] Mengubah Wording Promo menjadi Voucher, termasuk fungsi search voucher. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-235 | SLICING |  | [Slicing] Penyesuaian tampilan checklist di Shopping Bag. (Merubah warna centang menjadi merah sarinah) | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-236 | SLICING |  | [Slicing] Penyesuaian tampilan Other Fee di halaman Checkout. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-237 | SLICING |  | [Slicing] Update tampilan nama user menjadi running text untuk nama yang panjang, dan berhenti ketika hover | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-238 | SLICING |  | [Slicing] Penambahan pop up detail image di Product Detail | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-239 | SLICING |  | [Slicing] Integrasi Profile picture user default menggunakan inisial dan background coklat | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-240 | SLICING |  | [Slicing] Validasi discount pada product | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-241 | SLICING |  | [Slicing] Integrasi Profile picture Store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-242 | SLICING |  | [Slicing] Section Bestseller di Homepage | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-243 | SLICING |  | [Slicing] Take out Filter verified store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-244 | INTEGRASI |  | [Integrasi] Perbaikan bug sign in agar update otomatis tampil di header. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-245 | INTEGRASI |  | [Integrasi] Waiting for Payment— perbaikan Pay Now countdown refresh. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-246 | INTEGRASI |  | [Integrasi] Validasi pada fitur Change Payment. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-247 | API |  | [API] Penyesuaian tampilan Checkout terkait Other Fee. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-248 | API |  | [API] Perbaikan tampilan Virtual Account di Payment Method. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-249 | API |  | [API] Perbaikan API Shopping Bag (Checkbox). | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-250 | API |  | [API] Checking API Lazada. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-251 | SLICING |  | [Slicing] Terms of Service & Privacy Policy (Digabung menjadi 1) | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-252 | INTEGRASI |  | [Integrasi] Mengubah isi dari 'What’s On' di halaman All Categories, menjadi 'categori' | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-253 | INTEGRASI |  | [Integrasi] Section New user discount voucher di hide | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-254 | INTEGRASI |  | [Integrasi] Search ketika di enter akan masuk ke halaman search result | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-255 | API |  | [API] Pengembangan API Buy Again. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-256 | API |  | [API] Pengembangan API Login by Google. | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-257 | UI/UX |  | [UI/UX] Hide section voucher di home guest | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-258 | UI/UX |  | [UI/UX] Menambahkan scroll subkategori | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-259 | UI/UX |  | [UI/UX] Menambahkan scroll explore more | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-260 | UI/UX |  | [UI/UX] Term & Condition pada checkout diarahkan ke halaman privacy policy | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-261 | UI/UX |  | [UI/UX] Kode nomor voucher menggunakan sticky | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-262 | UI/UX |  | [UI/UX] Penambahan district & sub district di add new address | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-263 | UI/UX |  | [UI/UX] Keep exploring → tambah horizontal scrolling | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-264 | API |  | [API] Data provinsi & kota → tambah kecamatan & kelurahan | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-265 | INTEGRASI |  | [INTEGRASI] Cart menampilkan out of stock | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-266 | INTEGRASI |  | [INTEGRASI] Validasi profil incomplete -> redirect ke edit address | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-267 | INTEGRASI |  | [INTEGRASI] Bahasa in/en | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-268 | UI/UX |  | [UI/UX] Horizontal scroll sub category | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-269 | UI/UX |  | [UI/UX] Tambahan jam operasional (checkout warning bandara) | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-270 | SLICING |  | [SLICING] Horizontal scroll sub category | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-271 | SLICING |  | [SLICING] Tambahan jam operasional di address pickup at store | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-272 | SLICING |  | [SLICING] Responsive pop up voucher | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-273 | API |  | [API] Fungsi print AWB dan invoice | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-274 | API |  | [API] Category menjadi 3 level/infinite | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-275 | SLICING |  | [SLICING] Pop Up T&C di halaman checkout | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-276 | SLICING |  | [SLICING] semua filters responsive | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-277 | SLICING |  | [SLICING] next hide estimasi di opsi shipping, halaman checkout | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-278 | INTEGRASI |  | [INTEGRASI] ketika klik nama brand di cart maka akan melakukan filtered search | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-279 | INTEGRASI |  | [INTEGRASI] Ubah wording estimasi shipping menjadi "Harga Sudah Termasauk Biaya Asuransi" | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-280 | API |  | [API] membuat harga di other fee dinamis | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-281 | API |  | [BACKEND] Menyalakan opsi pembayaran CC | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-282 | API |  | [BACKEND] Update image QRIS menjadi 1024 | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100
FE-283 | SLICING |  | [SLICING] Hide Terms & Condition | 1 | Functional Test | Perform feature action | 1. Open Page 2. Interact with feature | Feature works as expected | As Expected | DONE | 100